## Slide 1: QUEEN ISABELLA MEMORIAL CAUSEWAY
TxDOT’s Plan Moving Forward

## Slide 2: Table of contents
7
8-26
27
28-35
36-52
4-6
53-56
Pharr District Facts
QIC Facts
QIC Bridge Elements
QIC Maintenance History
QIC Service Life Assessment
QIC 2013 Repairs
2017 Inspection Findings
1
2
3
4
5
6
7

## Slide 3: Table of contents
Questions
60-61
62
63
57-59
Fracture Critical Inspection
Reasons for QIC in Good Condition
TxDOT’s Plan Moving Forward
8
9
10
11

## Slide 4: Pharr District Facts
The Pharr District plans, designs, builds, operates, and maintains the state transportation system within its 8 counties. Pharr is a Coastal District with 14 International crossings and serves as a NAFTA corridor. The Pharr District is committed to ensuring the safety of the traveling public.
FY 2017 | 
Population | 1,385,195
Square Miles Area | 8,812
Lane Miles | 6,510 (+102)
Centerline Miles | 2,378
Daily Vehicle Miles | 19,283,619

## Slide 5: Pharr District Facts: On-System Bridges
State Bridge Total = 35,489
State Sufficiency Rating = 88%
Pharr District Total = 728
Sufficiency Rating = 92%
On-System inspections occur every two years. These inspections ensure all bridges open to traffic are safe. Reports are developed along with Follow-up Action reports to correct any significant issues to maintain bridge integrity. Currently, none of the Pharr District bridges are load rated. Thanks to ongoing maintenance efforts of our structures.

## Slide 6: Pharr District Facts: Off-System Bridges
State Bridge Total = 19,434
State Sufficiency Rating = 82%
Pharr District Total = 355
Sufficiency Rating = 84%
International Bridges = 14
  11 Public
  3 Private
Off-System bridges are inspected biannually and TxDOT helps by having them inspected for the County and City. There are currently 34 load zoned posted bridges within the Pharr District.

## Slide 7: QIC Facts
Connects Port Isabel to South Padre Island
Constructed between 1973 and 1974
2.36 miles long and 67.75’ wide (2 – 12’ lanes with inside and outside shoulders)
150 Pre-stressed Type 54 Concrete Beam Unit Spans (80’)
1 – 750’ Variable Depth Plate Girder three span continuous unit
(220’ – 310’ – 220’)
78’ Vertical clearance and 200’ horizontal clearance over Inter Coastal Waterway
2001 Vessel Impact – 320’ of Bridge removed and replaced
Cathodic Protection placed on sub-structure elements ~ 2011

## Slide 8
Bridge Elements

## Slide 9: Bridge Elements
Roadway Approach South Padre Island Side

## Slide 10: Bridge Elements
Roadway Approach Port Isabel Side

## Slide 11: Bridge Elements
Side View

## Slide 12: Bridge Elements
Type 54 Girders w/ Internal Concrete Diaphragm

## Slide 13
Multi-Column Bent

## Slide 14: Bridge Elements
Lower Tie Beam

## Slide 15: Bridge Elements
Pile Cap Footings

## Slide 16: Bridge Elements
750’ Variable Depth Steel Girder – 3 Girders

## Slide 17: Bridge Elements
Steel Girder with Internal Diaphragms

## Slide 18: Bridge Elements
Fender System

## Slide 19: Bridge Elements
Early Warning Collapse Detention

## Slide 20: Bridge Elements
Early Warning Collapse Detention

## Slide 21: Bridge Elements
Early Warning Collapse Detention

## Slide 22: Bridge Elements
Early Warning Collapse Detention

## Slide 23: Bridge Elements
Cathodic Protection showing damaged conduit and instrumentation

## Slide 24: Bridge Elements
Cathodic Protection

## Slide 25: Bridge Elements
Pile Jacket

## Slide 26: Bridge Elements
Navigation Lights

## Slide 27: QIC Maintenance History
FY | PROJECT DESCRIPTION | PROJECT COST
1997 | CATHODIC PROTECTION (BENT 19-24) | $478,000.00
1997 | REHAB/PAINT MAIN SPAN | $618,601.71
2001 | EMERGENCY REPAIRS (SPAN 29-33) | $5,918,012.88
2003 | CATHODIC PROTECTION | $3,117,394.00
 |  | $445,000.00
2003 | EARLY WARNING DETECTION | $842,861.00
2003 | PIER PROTECTION & FENDER SYSTEM | $3,262,255.00
 |  | $2,602,800.00
2003 | PIER PROTECTION & FENDER SYSTEM | $6,589,207.38
2004 | CATHODIC PROTECTION | $1,296,103.06
2007 | DOLPHIN & FENDER REPAIRS | $1,084,750.00
2009 | REPAIRS TO DECK SPAN #3 | $55,482.80
2010 | REHAB/PAINT MAIN SPAN/CATH PROTECTION | $3,940,365.06
2010 | REPLACE ILLUMINATION POLES/FIXT | $410,856.68
2010 | DOLPHIN & FENDER REPAIRS | $13,336.27
2011 | DOLPHIN & FENDER REPAIRS | $17,001.25
2012 | DOLPHIN & FENDER REPAIRS | $263,909.00
2013 | STRUCTURE REPAIRS, RAIL RETROFIT, SILANE | $2,811,843.96
 | TREATMENT, BEAM END REPAIR | 
 | PROJECTED TOTAL | $33,767,780.05

## Slide 28: QIC Service Life Assessment
Condition and Service Life Assessment (08/2009)
Based on the assessment findings, the Causeway is in good condition considering its age and service environment.

## Slide 29: QIC Service Life Assessment
Strategies For Extending the Life of the Structure:
Not employing any significant remediation efforts and only continuing with “routine” maintenance.
Employing both remediation and routine maintenance efforts to optimize the service life relative to cost.
Employing comprehensive remediation efforts to extend the service life of the beams and lower substructure elements to approximately that of the other elements.
Present estimated cost for QIC Replacement is ~ $ 125 M. (2009)
Service Life – bridge able to satisfy state legal load of 80,000 pounds. TxDOT’s goal is to avoid load posting of bridge.
No significant maintenance remedies performed for the first 20 years (1974 to 1995).

## Slide 30: QIC Service Life Assessment

## Slide 31: Option 1
Entails only normal maintenance efforts. Pre-stressed beams are the controlling element to yield a service life up to 2023. Total cost for this work is estimate at $6.9M.
Repair and paint steel girders ($4,500,000)
Repair non-functioning CP systems and broken appurtenances ($7,500)
Mill and replace seal coat at Steel Girder Spans 34 through 37 ($20,000)
Replace deteriorated anchor bolts and guard rails with a T-4 three-bolt railing system ($627,500)
Remove and replace deteriorated light standards ($680,000)
Install additional anode connections for thermally sprayed metalized coating at each pile cap ($22,500)
Coat all new and existing exposed anode connections for the thermally sprayed metalized coating with epoxy ($25,500)
Repair and paint exposed end connections for lateral tie roads ($117,000)
Completed VA BPM: 6207-63-00 and CSJ 0331-04-065 (2010 to 2013)

## Slide 32: Option 2
Includes all items captured in Option 1 and extends the service life an additional 10 to 15 years (2033). Again the pre-stressed beams are the controlling element. This includes the repair and repainting of the steel unit. This will be the fourth repainting effort (1983, 1995, 2010, 2020+ TBD). Total cost for this work is estimated at $14M.
Perform all items in Option 1 ($6,946,600) COMPLETED
Repair all existing spalls and major cracks elements utilizing conventional repair techniques ($1,203,750)
Repair end patches at all Type 54 beams ($600,000)
Apply a single application of a penetrating silane sealer to all exposed surfaces of the Type 54 beams and diaphragms ($802,500)
Repair blistered/delaminated areas of aluminum metalizing ($28,000)
Completed above work VIA CSJ 0331-04-065 (2010-2013)

## Slide 33: Option 3
Includes all items captured in Option 1 and 2 with additional remediation efforts for the beams and the existing cathodic protection system on the lower substructure to yield a service life up to 40 years (2043). Again the pre-stressed beams are the controlling element. Total cost for this work is estimated at $ 21.5 M.
Perform all items in Option 1 and 2, except as noted below, within a one or two year time period ($14,079,850) - COMPLETED
Apply CP system (zinc alloy thermal spray) to all Type 54 beams at ends, sides, and soffits (bottoms) for a distance of 3 feet from each end in approximately six to eight years following the first silane application ($2,000,000)
Apply second application of a penetrating silane sealer to beam and diaphragm surfaces without CP at same time CP system is applied ($802,500)
Replace zinc and aluminum alloy CP systems at lower substructure elements with new zinc alloy CP system at the same time CP system is applied to beams and pile caps ($4,587,500)

## Slide 34: Life Assessment Summary
The three options presented provides TxDOT a pathway for the QIC to systematically achieve an estimated service life of an additional 70 years (1973 to 2043).
Controlling bridge elements are the pre-stressed beam and substructure elements.
The QIC is in good condition considering its age and service environment.

## Slide 35: Things to Consider
TxDOT has committed to Option 3 to sustain serviceability to year 2043 and beyond.
Steel unit will receive its fourth paint system and a closer investigation with respect to nominal thicknesses need to be evaluated beyond further painting systems.
Re-application of the cathodic protection will need to be done but further investigation needs to be considered for the concrete beams.
A Life Cycle Cost will need to be performed beyond 2043 to evaluate a replacement benefit cost ratio. For now, it makes sense to maintain the QIC.
Routine Maintenance efforts are still required to sustain predicted service life estimate. Routine Maintenance efforts planned in FY 19 ~ $ 750 K.
Pharr District has understood the need for routine maintenance efforts and to address the right treatment at the right time before the treatment scope turns into replacement efforts. TxDOT’s maintenance efforts are reflective in the Service Life Assessment performed in 2009. The report serves as a guide for the QIC to reach and possibly exceed the estimated service life beyond in 2043.

## Slide 36
QIC 2013 Repairs

## Slide 37
QIC 2013 Repairs
Traffic Control

## Slide 38
QIC 2013 Repairs
Traffic Control

## Slide 39
Contractor using a movable working platform
QIC 2013 Repairs

## Slide 40
QIC 2013 Repairs
Exposed Pre-Stressed Strand – Corrosion Propagating

## Slide 41
Completed Concrete Structure Repairs (Beam)
QIC 2013 Repairs

## Slide 42
Span #1 WB Underside Bridge Deck Spalled concrete with exposed reinforcement.
QIC 2013 Repairs

## Slide 43
Armor Joint Plate - Deformation
QIC 2013 Repairs

## Slide 44
Armor Joint Repair – removal and replacement of armor joint
QIC 2013 Repairs

## Slide 45
Armor Joint – silicone sealant applied at join opening
QIC 2013 Repairs

## Slide 46
Beam End at Various Locations Deteriorated epoxy coating and exposed/corroded strands.
QIC 2013 Repairs

## Slide 47
QIC 2013 Repairs
Beam ends w/ Epoxy Coating

## Slide 48
Existing Rail Connection ‐ Typical Existing anchor bolts and hardware severely corroded.
QIC 2013 Repairs

## Slide 49
QIC 2013 Repairs
Completed bridge rail retrofit with SAP seal covers

## Slide 50
Existing concrete space at concrete diaphragm
QIC 2013 Repairs

## Slide 51
Completed Concrete Structure Repairs (Diaphrams)
QIC 2013 Repairs

## Slide 52
Colum Fiber Wrap – Bent #26 due to excessive cracking
QIC 2013 Repairs

## Slide 53: 2017 Inspection Findings
Beam Spall

## Slide 54: 2017 Inspection Findings
Spall

## Slide 55: 2017 Inspection Findings
Armor Joint

## Slide 56: 2017 Inspection Findings
Concrete Spalls | Square Footage
Top Deck | 24
Underside Deck | 16
Girders | 81
Bent Caps | 11
Diaphragms | 102
Pile Caps | 11
TOTAL | 245
As part of TxDOT’s Routine Safety Bi-Annual Inspections, a thorough inspection was performed with spalled concrete and compromised armor joints needing repair.
Description | Quantity | Unit | Cost | Subtotal
Traffic Control Barriers | 5 | MO | $20,000 | $100,000
Concrete Repair | 245 | SF | $1,000 | $245,000
Armor Joint Repair | 670 | LF | $600 | $402,000
 |  |  | TOTAL | ~$750,000
TxDOT plans to let a contract in FY 19 to address the above repairs. This project is considered routine maintenance.
Armor Joint Repair | Linear Footage
Armor Joint | 670

## Slide 57: Fracture Critical Inspection
Pack rust accumulation and weld at top flange and interior diaphragm
As part of TxDOT’s Routine Safety Bi-Annual Inspections, a thorough inspection was performed for the Steel Girder Unit.

## Slide 58: Fracture Critical Inspection
Minor Paint Failure at Bottom Flange

## Slide 59: Fracture Critical Inspection
Pack Rust at Bearing Plate

## Slide 60: Reasons for QIC in Good Condition
Tribute to our past engineers for having the foresight not to push design limits in a corrosive environment. Such simple implements include the following:
80’ Simple Spans – this is the practical and economical limit for a Type 54 Beam use. The ultimate design limit could reach up to 110’ thus placing more stress and strain on the beams and pre-stressing strands.
Concrete Diaphragms – no longer used in TxDOT bridge design, the internal diaphragms help distribute live and dead loads acting on the beams. Without placement at the quarter points, would place additional stress and strain on the beams.
Pre-stressed Pre-Cast Concrete Panels – a new concept of TxDOT bridge design at that time. The 4” deep concrete panels act as a forming mechanism with the remaining 4” of batch concrete placed to make the 8” deep slab. Little to no chance of corrosive sulfate penetrating into the steel which would lead to deck repair.

## Slide 61: Reasons for QIC in Good Condition
Multi-column Bents w/Tie Beams – the use of tie beams at mid height of the column and at the top of the pile footing caps help with load distribution and limiting cracks along the columns.
Cathodic Protection – the implementation of cathodic protection has prevented the substructure elements (steel reinforcement) from being compromised in a corrosive environment. Re-application of the sacrificial layer is needed to sustain the primary function of the bridge element.

## Slide 62: TxDOT’s Plan Moving Forward
The steel girder will be stripped and painted a fifth time ~ 2020. Concerns with reducing nominal thicknesses and tears in the welds.
Cathodic protection could be applied to the substructures and girders.
Life cycle cost needs to be investigated for continual maintenance remedies beyond 2043.
TxDOT plans to keep the QIC in good condition with strategic and time based maintenance efforts to prevent load posting and continue to serve as a life line to the traveling public and adjacent stakeholders.

## Slide 63
QUESTIONS?
Rex A. Costley, P.E.
Director of Maintenance
Rex.Costley@txdot.gov
956-702-6137